## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Introduction to project(Object Detection AI) | MUST HAVE | No Dependency | A Ramnarayan | 3- Completed
S1 | S1 | US-001 | Workflow Creation and Project Goal Document | MUST HAVE | Notion | A Ramnarayan | 3- Completed
S2 | S2 | US-001 | Document Discussion(Agile Template,Defect Tracker,Unit Testing) | MUST HAVE | No Dependency | A Ramnarayan | 3- Completed
S2 | S2 | US-001 | Use Case Research and Preparation | SHOULD HAVE | W3School | A Ramnarayan | 3- Completed
S3 | S3 | US-001 | Python practice Kit Completion | MUST HAVE | HackerRank | A Ramnarayan | 3- Completed
S4 | S4 | US-001 | AI ML practice kit completion | MUST HAVE | Coursera | A Ramnarayan | 3- Completed
S5 | S5 | US-001 | Project Discussion Module 1(Image Processing) | MUST HAVE | OpenCV | A Ramnarayan | 3- Completed
S6 | S6 | US-001 | Project Discussion Module 2(Workflow Automation and Optimization) | SHOULD HAVE | VS Code | A Ramnarayan | 2- In Progress
S7 | S7 | US-001 | Project Discussion Module 3(Integration with existing services) | SHOULD HAVE | Streamlit | A Ramnarayan | 2- In Progress
S8 | S8 | US-001 | Project Discussion Module 4(Testing and Deployment) | MUST HAVE | VS Code | A Ramnarayan | 2- In Progress
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 75 | 22 | 12 | 11 | 9 | 7 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | TID-01 | Introduction to project(Object Detection AI) | 2024-12-04 | 2024-12-06 | A Ramnarayan | Others | 3- Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TID-02 | Workflow Creation and Project Goal Document | 2024-12-07 | 2024-12-08 | A Ramnarayan | Design | 3- Completed | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TID-03 | Document Discussion(Agile Template,Defect Tracker,Unit Testing) | 2024-12-11 | 2024-12-11 | A Ramnarayan | Others | 3- Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TID-04 | Use Case Research and Preparation | 2024-12-12 | 2024-12-15 | A Ramnarayan | Others | 3- Completed | 6 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TID-05 | Python practice Kit Completion | 2024-12-16 | 2024-12-22 | A Ramnarayan | Coding | 3- Completed | 12 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TID-06 | AI ML practice kit completion | 2024-12-23 | 2024-12-29 | A Ramnarayan | Coding | 3- Completed | 7 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TID-07 | Project Discussion Module 1(Image Processing) | 2025-01-02 | 2025-01-06 | A Ramnarayan | Build | 3- Completed | 10 | 3 | 0 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TID-08 | Project Discussion Module 2(Workflow Automation and Optimization) | 2025-01-09 | 2025-01-13 | A Ramnarayan | Coding | 2- In Progress | 12 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TID-09 | Project Discussion Module 3(Integration with existing services) | 2025-01-16 | 2025-01-20 | A Ramnarayan | Integration Test | 2- In Progress | 12 | 4 | 3 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TID-10 | Project Discussion Module 4(Testing and Deployment) | 2025-01-23 | 2025-01-27 | A Ramnarayan | System Test | 2- In Progress | 8 | Day 1: 3; Day 2: 0; Day 3: 1; Day 4: 1; Day 5: 1; Day 6: 1; Day 7: 1
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | Lack of clarity on project requirements | Conducted a detailed discussion with mentors and team
Sprint 1 | Day 4 | Lack of clarity on specific project goals and workflow steps. | Conducted a team brainstorming session and reviewed the project requirements.
Sprint 2 | Day 6 | Agile template confusion | Conducted a meeting where all doubts were clarified by the mentor.
Sprint 2 | Day 7 | Difficulty in identifying all potential use cases due to incomplete information. | Conducted additional research and consulted online resources to fill gaps.
Sprint 2 | Day 9 | Confusion about prioritizing use cases for preparation. | Created a priority matrix to evaluate and rank use cases based on importance.
Sprint 3 | Day 12 | Difficulty in debugging Python practice code | Collaborated with Vaibhav and Akshaya to resolve issues
Sprint 4 | Day 16 | Object tracking taking longer than expected | Optimized queries with mentor support
Sprint 5 | Day 23 | Challenges integrating Object tracking with workflows | Scheduled team debugging session

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2024-11-04 | 2024-11-06 | Seenu Ananth | Reviewing documentation regularly | Assuming project requirements are clear | Participating in discussions and meetings | Scheduled a review session with team and mentors to clarify project goals.
2 | Sprint 3 | 2024-11-16 | 2024-11-22 | Akshaya | Prioritizing Python practice | Delaying review of tasks | Maintaining focus on coding | Achieved Python kit completion on time
3 | Sprint 4 | 2024-11-23 | 2024-11-29 | Vaibhav Sunil Shimpi | Preparing SQL practice | Rushing through AI/ML concepts. | Asking for help when stuck. | Completed AI/ML with support from the team
4 | sprint 5 | 2024-12-02 | 2024-12-06 | Vaibhav Sunil Shimpi,Seenu Ananth,Akshaya | Participating in Module 1 discussions | Delaying Object Tracking exploration | Collaborating on Object tracking strategies | Completed Object tracking prototypes and received team feedback for improvements.